## Import_Ted
任务 | WBS_ID | Predecessors | ActivityType | ScheduleStartDate | ScheduleEndDate | Owner | 部门
Dell-MeetingCam project | 0 |  | Project
Phase 1: Risk Analysis | 1 |  | Phase
Phase 2: Qualification Plan | 2 |  | Phase
Phase 3: DVT1 | 3 |  | Phase
Phase 4: DVT2 | 4 |  | Phase
Phase 5: Pilot | 5 |  | Phase
Phase 6: Ramp-up | 6 |  | Phase
Project master schedule | 6.1.1 |  | Task | 2026-01-20 | 2026-01-25 | 10007327 | MIPM
All NPI issues closure | 6.2.1 |  | Task | 2026-02-15 | 2026-02-20 | 10007327 | MIPM
CTQ report | 6.2.2 |  | Task | 2026-02-15 | 2026-02-20 | 10007327 | DQA
Safe launch report | 6.2.3 |  | Task | 2026-02-15 | 2026-02-20 | 10007327 | ERD
AQP compliance audit | 6.2.4 |  | Task | 2026-02-15 | 2026-02-20 | 10007327 | ENG
Phase 6 exit: NPI phase exit review meeting | 6.3.1 |  | Task | 2026-02-15 | 2026-02-20 | 10007327 | MIPM
Project master schedule | 5.1.1 |  | Task | 2025-11-25 | 2025-11-30 | 10007327 | MIPM
Pilot build detail plan | 5.1.2 |  | Task | 2025-12-15 | 2025-12-20 | 10007327 | MIPM
NUDD & mitigation action | 5.2.1 |  | Task | 2025-12-25 | 2025-12-30 | 10007327 | ERD
Supply chain map | 5.3.1 |  | Task | 2025-12-15 | 2025-12-20 | 10007327 | PUR
Sub-tiers issues closure | 5.3.2 |  | Task | 2025-12-15 | 2025-12-20 | 10007327 | SQE
Test coverage review | 5.4.1 |  | Task | 2025-12-15 | 2025-12-20 | 10007327 | DQA
Process audit | 5.4.2 |  | Task | 2025-12-25 | 2025-12-30 | 10007327 | DQA
CTQ report | 5.4.3 |  | Task | 2025-12-25 | 2025-12-30 | 10007327 | DQA
Safe launch report | 5.4.4 |  | Task | 2025-12-25 | 2025-12-30 | 10007327 | ERD
AQP release for MP | 5.5.1 |  | Task | 2025-12-25 | 2025-12-30 | 10007327 | ENG
System NPI issue review | 5.6.1 |  | Task | 2026-01-15 | 2026-01-20 | 10007327 | ERD
Phase 5 exit | 5.6.2 |  | Task | 2026-01-15 | 2026-01-20 | 10007327 | MIPM
Project master schedule | 4.1.1 |  | Task | 2025-05-15 | 2025-05-20 | 10007327 | MIPM
DVT2 build detail plan | 4.1.2 |  | Task | 2025-08-15 | 2025-08-20 | 10007327 | MIPM
NUDD & mitigation action | 4.2.1 |  | Task | 2025-08-27 | 2025-09-01 | 10007327 | ERD
Supply chain map | 4.3.1 |  | Task | 2025-08-15 | 2025-08-20 | 10007327 | PUR
Tooling qualification | 4.3.2 |  | Task | 2025-10-27 | 2025-11-01 | 10007327 | PUR
Sub-tier qualification | 4.3.3 |  | Task | 2025-08-15 | 2025-08-20 | 10007327 | SQE
Test coverage review | 4.4.1 |  | Task | 2025-08-27 | 2025-09-01 | 10007327 | DQA
Safe launch report | 4.4.2 |  | Task | 2025-08-27 | 2025-09-01 | 10007327 | ERD
CTQ report | 4.4.3 |  | Task | 2025-10-27 | 2025-11-01 | 10007327 | DQA
Process audit | 4.4.4 |  | Task | 2025-08-27 | 2025-09-01 | 10007327 | DQA
Process equipment & fixture review | 4.4.5 |  | Task | 2025-08-15 | 2025-08-20 | 10007327 | ENG
PPID label validation | 4.4.6 |  | Task | 2025-08-15 | 2025-08-20 | 10007327 | ENG
Process turn A readiness review | 4.4.7 |  | Task | 2025-11-10 | 2025-11-15 | 10007327 | MIPM
AQP for pilot build | 4.5.1 |  | Task | 2025-10-27 | 2025-11-01 | 10007327 | ENG
System DVT2 issue review | 4.6.1 |  | Task | 2025-10-27 | 2025-11-01 | 10007327 | ERD
System matching review | 4.6.2 |  | Task | 2025-10-27 | 2025-11-01 | 10007327 | ERD
Phase 4 exit | 4.7.1 |  | Task | 2025-11-20 | 2025-11-25 | 10007327 | MIPM
Project master schedule | 3.1.1 |  | Task | 2025-03-15 | 2025-03-20 | 10007327 | MIPM
DVT1 build detail plan | 3.1.2 |  | Task | 2025-03-15 | 2025-03-20 | 10007327 | MIPM
NUDD & mitigation action | 3.2.1 |  | Task | 2025-03-27 | 2025-04-01 | 10007327 | ERD
Supply chain map | 3.3.1 |  | Task | 2025-03-15 | 2025-03-20 | 10007327 | PUR
Tooling status update | 3.3.2 |  | Task | 2025-03-15 | 2025-03-20 | 10007327 | PUR
Sub-tier qualification | 3.3.3 |  | Task | 2025-03-15 | 2025-03-20 | 10007327 | SQE
Test coverage review | 3.4.1 |  | Task | 2025-03-27 | 2025-04-01 | 10007327 | DQA
Process audit | 3.4.2 |  | Task | 2025-03-27 | 2025-04-01 | 10007327 | DQA
CTQ report | 3.4.3 |  | Task | 2025-03-27 | 2025-04-01 | 10007327 | DQA
Safe launch report | 3.4.4 |  | Task | 2025-03-27 | 2025-04-01 | 10007327 | ERD
Process equipment & fixture review | 3.4.5 |  | Task | 2025-03-27 | 2025-04-01 | 10007327 | ENG
AQP for DVT2 build | 3.5.1 |  | Task | 2025-03-10 | 2025-03-15 | 10007327 | ENG
System DVT1 issue review | 3.6.1 |  | Task | 2025-03-10 | 2025-03-15 | 10007327 | ERD
System matching reivew | 3.6.2 |  | Task | 2025-05-05 | 2025-05-10 | 10007327 | ERD
Phase 3 exit | 3.7.1 |  | Task | 2025-05-10 | 2025-05-15 | 10007327 | MIPM
Project master schedule | 2.1.1 |  | Task | 2025-01-20 | 2025-01-25 | 10007327 | MIPM
NUDD & mitigation plan | 2.2.1 |  | Task | 2025-03-05 | 2025-03-10 | 10007327 | ERD
Supply chain map | 2.3.1 |  | Task | 2025-03-05 | 2025-03-10 | 10007327 | PUR
Tooling plan | 2.3.2 |  | Task | 2025-03-05 | 2025-03-10 | 10007327 | PUR
Sub-tier qualification plan | 2.3.3 |  | Task | 2025-03-05 | 2025-03-10 | 10007327 | SQE
Test plan | 2.4.1 |  | Task | 2025-03-05 | 2025-03-10 | 10007327 | DQA
CTQ plan | 2.4.2 |  | Task | 2025-03-05 | 2025-03-10 | 10007327 | DQA
Process equipment & fixture plan | 2.4.3 |  | Task | 2025-03-05 | 2025-03-10 | 10007327 | ENG
AQP for DVT1 build | 2.5.1 |  | Task | 2025-03-10 | 2025-03-15 | 10007327 | ENG
system matching review | 2.6.1 |  | Task | 2025-04-15 | 2025-04-20 | 10007327 | ERD
Phase 2 exit | 2.7.1 |  | Task | 2025-03-10 | 2025-03-15 | 10007327 | MIPM
Kick-off meeting | 1.1.1 |  | Task | 2024-12-31 | 2025-01-05 | 10007327 | MIPM
Project road map | 1.1.2 | 1.1.1 | Task | 2024-12-31 | 2025-01-05 | 10007327 | MIPM
Set up a project team | 1.1.3 | 1.1.2 | Task | 2024-12-31 | 2025-01-05 | 10007327 | MIPM
Initiate NUDD & mitigation plan | 1.2.1 | 1.1.3 | Task | 2025-01-15 | 2025-01-20 | 10007327 | ERD
Lesson learn review | 1.2.2 | 1.2.1 | Task | 2025-01-15 | 2025-01-20 | 10007327 | ERD
Phase 1 exit | 1.3.1 | 1.2.2 | Task | 2025-01-15 | 2025-01-20 | 10007327 | MIPM